PACKAGING DEVELOPMENT TRACKER

OPERATIONAL GOVERNANCE, RACI AUTHORITY MATRIX & WORKFLOW MANUAL

Document Version: 2.0  ·  Scope: NPD & EPD Packaging  ·  Brief to Launch Pipeline

# 1. Executive Overview & Purpose

The Packaging Development Tracker is an enterprise-grade stage-gate management system designed to govern the end-to-end commercial packaging rollout from initial marketing brief to final market launch. It standardizes technical specifications, eliminates inter-departmental communication bottlenecks, enforces quality sign-off gates, and tracks real-time milestone lead times across all physical packaging components.

Core Business Objectives:  (1) Achieve 100% On-Time-In-Full (OTIF) launch delivery; (2) Lock dielines and specifications early to prevent artwork rework; (3) Eliminate regulatory text non-compliance; (4) Provide full auditability for every stage transition and technical specification modification.

# 2. System Access Authority (Application Roles & Permissions)

The digital application enforces strict Role-Based Access Control (RBAC). User permissions are split into four tiers to protect project integrity while offering transparent visibility across functional stakeholders:

| System Action / Feature | Viewer | Editor | Admin | Super Admin |
| --- | --- | --- | --- | --- |
| View Analytics Dashboard, Tracker & Gantt | YES | YES | YES | YES |
| Export Project Data to CSV Spreadsheet | YES | YES | YES | YES |
| Search, Filter by Stage, Status & Lead Time | YES | YES | YES | YES |
| Create New Project (+ New Project Modal) | NO | YES | YES | YES |
| Advance Component / Project Stage | NO | YES | YES | YES |
| Edit Technical Specs (Dieline, Dims, GSM, Finish) | NO | YES | YES | YES |
| Edit Inline FG Code & Supplier Names | NO | YES | YES | YES |
| Modify Project Details (SKU, Type, Category) | NO | YES | YES | YES |
| Adjust Brief Date & Auto-Recalculate Milestones | NO | YES | YES | YES |
| Mark Project as Launched (Commercial Live) | NO | YES | YES | YES |
| Delete Inactive / Cancelled Projects | NO | YES | YES | YES |
| Revoke / Rollback Stage (Gate Failure Action) | NO | NO | YES | YES |
| Live Audit Activity Stream & Unread Badges | NO | NO | YES | YES |

• Viewer Role (All General Users & Cross-Functional Observers): Has real-time, transparent visibility into project schedules, upcoming milestones, and packaging specifications. Designed for sales, field marketing, finance, and plant operations.

• Editor Role (Packaging Engineers, Project Leads): Has full day-to-day operational execution rights. Responsible for entering technical drawings, selecting resin/substrate grades, updating suppliers, logging completed stages, and advancing materials.

• Admin Role (Department Heads, Packaging Leadership): Holds supervisory and governance authority. Contains all Editor capabilities plus the critical Stage Revocation Gate. If a test fails or artwork is rejected by legal, only an Admin can push a project backward. Admins also review the real-time activity stream to audit who completed each milestone and when.

# 3. Cross-Functional Authority & Governance (RACI Matrix)

To ensure clear accountability across the 10-stage development pipeline, every activity is mapped to the standard RACI governance framework across 7 company functions:

A = Accountable: The single decision-maker who approves the phase. Only ONE "A" per stage.
R = Responsible: The "doers" who execute the deliverables and complete the physical work.
C = Consulted: Two-way communication; subject matter experts whose sign-off is mandatory.
I = Informed: One-way communication; stakeholders kept updated on dates and progress.

| Stage / Gate | Brand Mgmt | Packaging | Supply Chain | Factory | Procurement | Quality / Reg | Network Planner |
| --- | --- | --- | --- | --- | --- | --- | --- |
| 1. Brief | A | R | C | I | C | C | I |
| 2. Sample | C | R | I | I | C | C | I |
| 3. Trial | I | C | R | R | I | C | I |
| 4. KLD | C | R | I | I | C | C | I |
| 5. Artwork | A | R | I | I | I | C | I |
| 6. VPDF | A | R | I | I | I | C | I |
| 7. Printing | I | C | I | I | R | A | I |
| 8. Dispatch | I | I | R | C | A | I | C |
| 9. Connectivity | I | C | A | C | C | I | R |
| 10. Launch | A | C | R | R | C | C | R |

# 4. Stage-by-Stage Quality Gates & Responsibilities

## Stage 01: Packaging Development Brief (Brief)  ·  Lead Time: Day 0 — Start

• Stage Ownership: Brand Management + Packaging  —  Formal kick-off. All functional requirements frozen and signed off.

• Mandatory Inputs: Marketing brief, Consumer insight, Benchmark samples, Regulatory requirements, Cost target

• Key Deliverables: Signed Packaging Brief, Project ID raised, Supplier RFQ list

• Quality Gate Checklist: [ ✓ ] Brief signed by Brand, Packaging & SC  |  [ ✓ ] Cost target aligned  |  [ ✓ ] Regulatory sign-off checklist  |  [ ✓ ] Pack format confirmed

## Stage 02: Prototype / T1 Sample (Sample)  ·  Lead Time: +5 days from Brief

• Stage Ownership: Packaging + Supplier  —  First physical prototype by supplier against approved brief specifications.

• Mandatory Inputs: Signed brief, Material spec, Tooling instructions, Benchmark reference

• Key Deliverables: T1 prototype samples, Sample evaluation report, Deviation log

• Quality Gate Checklist: [ ✓ ] Dimensions within ±0.5mm  |  [ ✓ ] Material grade confirmed  |  [ ✓ ] Colour Pantone matching  |  [ ✓ ] Drop test 1.2m 6 faces  |  [ ✓ ] Stackability OK

## Stage 03: Factory Line Trial (Trial)  ·  Lead Time: +7 days from Sample

• Stage Ownership: Factory + Packaging + SC  —  Pack run on actual production line to validate machine compatibility.

• Mandatory Inputs: Approved T1 sample, Machine speed target, SOP draft

• Key Deliverables: Trial report, Machine speed sign-off, SOP v1.0

• Quality Gate Checklist: [ ✓ ] Line speed ≥ OEE target  |  [ ✓ ] Seal integrity passed  |  [ ✓ ] Label placement ±1mm  |  [ ✓ ] Fill weight ±2g  |  [ ✓ ] Defect rate <0.5%

## Stage 04: Key Line Data — Spec Lock (KLD)  ·  Lead Time: +3 days from Trial

• Stage Ownership: Packaging + Quality + Procurement  —  All technical specs FROZEN. KLD sheet issued to artwork studio.

• Mandatory Inputs: Trial-approved dimensions, Barcode zone, Legal text, Nutrition panel

• Key Deliverables: Signed KLD sheet, Final dieline, GS1 barcode registration

• Quality Gate Checklist: [ ✓ ] All dimensions locked  |  [ ✓ ] GS1 barcode confirmed  |  [ ✓ ] Legal text approved  |  [ ✓ ] Dieline approved  |  [ ✓ ] Colour locked (CMYK + Pantone)

## Stage 05: Artwork Development & Approval (Artwork)  ·  Lead Time: +5 days from KLD

• Stage Ownership: Brand + Packaging + Regulatory  —  Creative artwork developed, proofed and approved through structured rounds.

• Mandatory Inputs: Approved KLD, Brand guidelines, Legal claims, Nutritional data

• Key Deliverables: Print-ready artwork (PDF/AI), Signed approval form, Colour swatch sign-off

• Quality Gate Checklist: [ ✓ ] Round 1 — layout & hierarchy  |  [ ✓ ] Round 2 — legal & regulatory  |  [ ✓ ] Round 3 — colour & typography  |  [ ✓ ] Brand sign-off  |  [ ✓ ] Regulatory & QA sign-off

## Stage 06: Virtual PDF / Digital Proof Sign-off (VPDF)  ·  Lead Time: +2 days from Artwork

• Stage Ownership: Packaging + Brand + Quality  —  Digital soft-proof reviewed against physical colour target before print job released.

• Mandatory Inputs: Print-ready artwork, Colour target swatch, Substrate sample

• Key Deliverables: Signed VPDF approval form, Press release instruction

• Quality Gate Checklist: [ ✓ ] Colour delta ΔE < 2 vs Pantone  |  [ ✓ ] Barcode grade ≥ C (ISO 15415)  |  [ ✓ ] All text legible  |  [ ✓ ] VPDF signed by Brand + Packaging + QA

## Stage 07: Print Production / Bulk Manufacture (Printing)  ·  Lead Time: Digital: 10d · Flexo: 20d · Gravure: 35d

• Stage Ownership: Supplier + Procurement + Quality  —  Commercial bulk print run. Lead time depends on print process.

• Mandatory Inputs: Signed VPDF, PO from Procurement, Supplier schedule

• Key Deliverables: Bulk packaging material, COA, QC inspection report

• Quality Gate Checklist: [ ✓ ] First-off press check signed  |  [ ✓ ] Colour check vs swatch  |  [ ✓ ] Barcode scan 100% units  |  [ ✓ ] Quantity verified vs PO  |  [ ✓ ] Incoming QC passed

## Stage 08: Dispatch to Factory / DC (Dispatch)  ·  Lead Time: +4 days from Printing

• Stage Ownership: Supply Chain + Logistics + Procurement  —  Packaging material dispatched from supplier to factory or DC.

• Mandatory Inputs: Delivery schedule, Truck booking, Factory goods-in slot

• Key Deliverables: GRN (Goods Receipt Note), Stock in WMS, QA release in SAP

• Quality Gate Checklist: [ ✓ ] Quantity matches PO  |  [ ✓ ] No transit damage  |  [ ✓ ] Conditions met  |  [ ✓ ] Scanned into WMS  |  [ ✓ ] QA release updated

## Stage 09: Connectivity / System Setup (Connectivity)  ·  Lead Time: +4 days from Dispatch

• Stage Ownership: Supply Chain + IT + Factory + Network Planner  —  All system masters live — SAP codes, BOM, DRP parameters, replenishment rules.

• Mandatory Inputs: GRN confirmation, Final approved material, Master data form

• Key Deliverables: SAP material code active, BOM updated, DRP live, Distribution confirmed

• Quality Gate Checklist: [ ✓ ] Material code in SAP  |  [ ✓ ] BOM updated for all SKUs  |  [ ✓ ] Min/max set in DRP  |  [ ✓ ] Distribution network confirmed  |  [ ✓ ] Forecast updated in S&OP

## Stage 10: Market Launch (Launch)  ·  Lead Time: Manual — mark actual date

• Stage Ownership: Brand + Supply Chain + Factory  —  First commercial unit produced and sold. Launch date manually confirmed.

• Mandatory Inputs: Production schedule, Commercial stock, Trade plan, QA release

• Key Deliverables: First sale confirmation, Post-launch dashboard, PLR report

• Quality Gate Checklist: [ ✓ ] First commercial run complete  |  [ ✓ ] Stock in DC  |  [ ✓ ] Sales team briefed  |  [ ✓ ] Customer notifications sent  |  [ ✓ ] 30-day PLR scheduled

# 5. Automated Tracking Engine & Operating Rules

1. Multi-Material Component Tracking: Packaging for a single product typically requires multiple materials (e.g. Primary printed film, mono carton box, corrugated shipper). Each material can be advanced independently to reflect physical supplier delivery realities.

2. Synchronized Project Gating (Slowest Component Rule): The overall Project Stage is dynamically locked to the MINIMUM stage among all its active materials. A project cannot be launched until every packaging component has completed Stage 09 (Connectivity).

3. Dynamic Printing Lead Times: Stage 07 (Printing) lead times are dynamically calculated based on the printing substrate technology chosen: Digital Print (10 calendar days), Flexo Print (20 calendar days), Gravure Print (35 calendar days).

4. Automated Variance & Risk Tracking: The tracker continuously evaluates current date against original milestone dates. If actual completion exceeds planned lead time, the project automatically flags as "At Risk" or "Delayed", calculating the exact slip days.

5. Immutable Audit Trail: Every stage advancement, stage revocation, FG code update, or specification change is recorded with the user's name, email, timestamp, and variance delta in the live audit log.

# 6. Stakeholder Sign-Off & Approval Block

By signing below, the functional department heads confirm adherence to the RACI authorities, quality gate checks, and stage-advance operating procedures detailed in this document.

| Head of Brand Management: Signature: ___________________________ Date: _______________________________ | Head of Packaging Development: Signature: ___________________________ Date: _______________________________ |
| --- | --- |
| Head of Supply Chain & Logistics: Signature: ___________________________ Date: _______________________________ | Head of Quality & Regulatory: Signature: ___________________________ Date: _______________________________ |